## START HERE
GET STARTED
This spreadsheet is designed to help guide you through the stakeholder assessment steps and make sure you understand what will be involved in each step. Review the below and then spend time on the "Stakeholder Assessment Template" tab in this spreadsheet to familiarize yourself with the details.
Introduction
A stakeholder is any individual, group, or organization that can affect, be affected by, or perceive itself to be affected by a change. This Stakeholder Assessment template helps Okta's Customer team in identifying the groups that are key to the successful adoption of upcoming changes from Okta's implementation, identifying champion(s) in each of those groups, and assessing each champion's level of awareness, support, and influence in the project. This assessment will help determine how best to involve and communicate with each of these stakeholder champions.
Prerequisites
It is recommended you have an understanding of the below in order to complete your Stakeholder Assessment: - The impacted stakeholder groups and associated champions within those groups
Instructions
1. This Stakeholder Assessment template should be initiated during the “Plan” phase and updated throughout the “Design” phase of the Okta Deploy Methodology. 2. Once the Okta implementation design is better understood, Okta's Customer PM, Okta Business Analyst (if staffed), or designee should perform the Stakeholder Assessment with other project team members using the "Stakeholder Assessment Template" tab in this workbook as a guide. 3. Okta's Customer PM, Okta Business Analyst (if staffed), or designee should list the stakeholder groups likely to be impacted by the project, list the individuals who will champion the change, and rate each stakeholder champion's level of awareness, support, and influence in the project. The stakeholder champions should generally include, at a minimum, your Okta admin, additional IT contacts, and business application owners, but also be sure to look beyond the people on or involved with the project team as well, such as downstream impacted users in a B2B or B2C use case.
Best Practices
It is recommended that once the Stakeholder Assessment is drafted, it is reviewed with stakeholder champions to promote and encourage participation and involvement.
Subsequent Steps
1. Once Okta's Customer PM, Okta Business Analyst (if staffed), or designee has completed the Stakeholder Assessment, it should be discussed with the entire customer project team to plan how to engage each stakeholder champion appropriately. 2. Okta's Customer PM, Okta Business Analyst (if staffed), or designee should then begin executing the plan.

## Stakeholder Assessment Template
Stakeholder Group | Stakeholder Champion Name | Stakeholder Champion's Title/Role | Level of Awareness | Level of Support | Level of Influence | Engagement Plan
<Information Technology> |  |  | High | High | High
<Information Security/Risk> |  |  | Medium | Medium | Medium
<Business Owners> |  |  | Low | Low | Low
<Project Management Office> |  |  | Unknown | Unknown | Unknown
<Engineering>
<Human Resources>
<Help Desk>
<Operations>
<Finance & Accounting>
<Change Management>
<Communications>
<Sales & Marketing>
<Legal>
<Okta's Customer's Customer>
<Etc..>