## START HERE
GET STARTED
This spreadsheet is designed to help guide you through the Change Adoption Measurement steps and make sure you understand what will be involved in each step. Read the introductory information below and then spend time on the "Change Adoption Measurement Plan Template" tab in this spreadsheet to familiarize yourself with the details.
Introduction
This Change Adoption Measurement Plan template is to assist Okta's Customer team in determining the metrics and measurements to be used to indicate adoption levels of the Okta changes. The plan should detail the metrics/measurements required and when, how, how often, Etc.. the data will be collected. The feedback collected will help in developing corrective action plans and post-implementation change management activities.
Prerequisites
It is recommended you have an understanding of the below in order to complete your Change Adoption Measurement Plan: -The key business objectives of the Okta implementation -The target metric or measurements for each objective -Any existing tools and reports that can be leveraged
Instructions
1. This Change Adoption Measurement Plan template should be initiated during the “Build” phase of the Okta Deploy Methodology. 2. Once the change impacts are understood from the change impact analysis, Okta's Customer PM, Okta Business Analyst (if staffed), or designee should develop the Change Adoption Measurement Plan with project sponsors using the "Change Adoption Measurement Plan Template" tab in this workbook as a guide. 3. Okta's Customer PM, Okta Business Analyst (if staffed), or designee should list the key business objectives and their associated metrics and measurements required, along with when, how, and how often the data will be collected.
Best Practices
Examples of popular data collection methods for feedback include surveys, focus groups, interviews, and reports. Diagnosing and managing any adoption resistance is an ongoing process and requires close relationships with the primary sponsor and key stakeholders. It is important to determine the root cause of resistance and develop plans to address the root cause. If your organization has an assigned Okta Customer Success Manager, consult with them to assist with what metrics are commonly reported and how the data can be provided or collected.
Subsequent Steps
1. Once Okta's Customer PM, Okta Business Analyst (if staffed), or designee has completed the Change Adoption Measurement Plan with project sponsors, it should be reviewed with the entire customer project team. 2. Developing materials to measure change adoption, such as survey creation, interview questions, report building, should be added to the overall End User Change Management Plan. 3. After go-live, Okta's Customer PM, Okta Business Analyst (if staffed), or designee should also begin executing this Change Adoption Measurement Plan.

## Change Adoption Measurement Pla
Objective | Metric/Measurement | Minimum Metric for Success | Data Collection Method | Data Collection Method Content Creator | Initial Data Collection Period | Frequency of Data Collection | Comments
<User registration Active users MFA enrollment Etc.> | <% of users registered # unique users last 30 days % of users signed-up for MFA % customer satisfaction during enrollment Etc.> | <95% internal employees 45% users by end of 2 days Etc.> | <Survey Focus Group Interviews Metrics Reports Etc.> |  | <1 week post go-live 2 months post go-live Etc.> | <Every 30 days for first 3 months Every week for first month Etc.>