## START HERE
GET STARTED
This spreadsheet is designed to help guide you through the change management steps and make sure you understand what will be involved in each step. Review the below and then spend time on the "Change Management Plan Template" tab in this spreadsheet to familiarize yourself with the details.
Introduction
This End User Change Management Plan template helps Okta's Customer team to create a planned and structured approach to align their organization and their end users for upcoming changes from Okta's implementation.
Prerequisites
It is recommended you have a general understanding of the below in order to complete your End User Change Management Plan: - What Apps are planning to utilize Okta - What Okta products and features are planning to be implemented (e.g. MFA, SSO, etc.) - What types of end users would be impacted (internal, external, employees, contractors, etc.)
Instructions
1. This Change Management Plan template should be initiated during the design phase of the Okta Deploy Methodology. 2. Once the Okta implementation design is better understood, Okta's Customer PM, Okta Business Analyst (if staffed), or designee should create the End User Change Management Plan using the "Change Management Plan Template" tab in this workbook as a guide for standard change management activities. 3. This Change Management Plan should be integrated into the project's overall project plan, but it could also stand alone if a different customer team will be managing it.
Best Practices
Prioritizing and performing proper change management planning and execution helps to make projects more successful by focusing on important, though often overlooked, aspects of change—preparing individuals for change, and generating buy-in. Past successful Okta roll-outs and adoptions had the following approaches: Small, incremental go-lives, key application that drove/forced end-user usage, early and frequent communication.
Subsequent Steps
1. Once Okta's Customer PM, Okta Business Analyst (if staffed), or designee has received approval on this End User Change Management Plan, it should be provided to the Okta PM to adjust any implementation date changes as necessary. 2. Okta's Customer PM, Okta Business Analyst (if staffed), or designee should also begin executing this End User Change Management Plan. NOTE: Once the End User Communications and End User Training Plans are developed, those associated activities and dates should also be added to this Change Management Plan and/or the project's overall project plan.

## Change Management Plan Template
Task |  | Description/Notes | Due Date | Owner | Status | Okta Provided Tool/Template
End User Change Management Approach
| Develop End User Change Management Plan | This End User Change Management Plan template has standard change management activities that should be in your Change Management Plan. |  |  |  | This worksheet
Review and Approve End User Change Management Plan
Stakeholder Assessment
| Identify Stakeholders and Understand Influence and Impact | This is the process of identifying the groups that are key to the successful adoption of upcoming changes from Okta's implementation, identifying champions in each of those groups, and assessing each champion's level of awareness, support, and influence in the project. This assessment will help determine how best to involve and communicate with each of these stakeholder champions throughout. The stakeholder champions should generally include, at a minimum, your Okta admin, additional IT contacts, and business application owners. |  |  |  | https://support.okta.com/resource/EUAT_Assessment_Templates
Organizational Readiness
| Assess Organization’s Capacity for Change | This is the process of gaugin the organization's overall readiness for change. It allows the team to identify high-risk areas early in the project. It should be reassessed throughout the project, especially prior to the “Go-Live” phase, to confirm that the organization is prepared to accept the changes. |  |  |  | https://support.okta.com/resource/EUAT_Organizational_Readiness_Assessment_Template
Change Impact Assessment
| Assess Impact of Change to Organization | This is the process of determining how different end-user populations (like employees, contractors, and partners) are likely to be affected by the changes, and to define mitigating steps to address the impacts. |  |  |  | https://support.okta.com/resource/EUAT_Change_Impact_Analysis_Template
End User Communications (for internal and external users, as applicable)
| Develop End User Communications Plan | This is a plan that details the communication(s) needed to inform impacted end users on what they can expect from Okta, to provide important information about any actions end users will be expected to take, and/or to communicate changes to end users' workflow. The content should raise awareness and highlight the benefits of Okta as well. This plan will help determine the communication materials, objectives, audiences, approach, and timeline needed. |  |  |  | https://support.okta.com/resource/EUAT_End_User_Communications_Plan_Template
| Develop End User Comms/Emails | These are the actual communications that will be used to inform end users. |  |  |  | https://support.okta.com/resource/EUAT_End_User_Email_Communication_Templates
Review and Approve End User Comms/Emails
Deploy Comms following End User Communications Plan
End User Training (for internal and external users, as applicable)
| Develop End User Training Plan | This is a plan that details the training needed to educate impacted end users, to ensure they are set up for success with Okta. This plan will help determine the training materials, objectives, audiences, approach, and timeline needed. |  |  |  | https://support.okta.com/resource/EUAT_End_User_Training_Plan_Template
| Develop End User Training Materials | These are the actual trainings that will be used to educate end users. |  |  |  | https://support.okta.com/resource/EUAT_End_User_FAQs
Review and Approve End User Training Materials
Deploy Training following End User Training Plan
Incorporate Any FAQs Received from End Users into Future Training Materials
End User Support (for internal and external users, as applicable)
| Develop End User Support Plan | This is a plan that details how the end users will get help when Okta has been implemented. The plan should detail the support tool/method, the people supporting it, the types of tasks supported, escalation paths if required, etc. |  |  |  | https://support.okta.com/resource/EUAT_End_User_Support_Plan_Template
| Develop End User Support Materials (As Necessary) | These are the materials that will be used by the people enlisted to fulfill the support plan.
Review and Approve End User Support Materials
Deploy Support following End User Support Plan
Document and Incorporate Any Lessons Learned into Future Implementations
End User Change Adoption Measures
| Develop End User Change Adoption Measurement Plan | This is the plan that details the metrics and measurements to be used to indicate adoption levels of the Okta changes. The plan should detail the metrics and measurements required, and when, how, and how often the data will be collected. The feedback collected will help develop corrective action plans and post-implementation change management activities. |  |  |  | https://support.okta.com/resource/EUAT_Change_Adoption_Measurement_Plan_Template
| Develop End User Change Adoption Measurement Materials | These are the actual materials that will be used to gather the metrics and measurements of adoption. |  |  |  | https://support.okta.com/help/s/end-user-adoption-toolkit/end-user-adoption-measurements?language=en_US
Review and Approve End User Change Adoption Measurement Materials
Deploy Measurements following End User Change Adoption Measurement Plan
Document and Incorporate Any Lessons Learned into Future Implementations
Change Sustainment
| Incorporate Okta Training into New Hire Onboarding, as Appropriate | This is the process of incorporating Okta training into your new hire onboarding path