## START HERE
GET STARTED
This spreadsheet is designed to help guide you through the End User Support steps and make sure you understand what will be involved in each step. Review the below and then spend time on the "End User Support Plan Template" tab in this spreadsheet to familiarize yourself with the details.
Introduction
This End User Support Plan template helps Okta's Customer team in identifying how the end users will get help when Okta has been implemented. The plan should detail the support tool/method, the people supporting it, the types of tasks supported, escalation paths if required, etc.
Prerequisites
It is recommended you have an understanding of the below in order to complete your End User Support Plan: -The groups of end users impacted -The types of questions and support end users may require -Any existing tools or teams that can be leveraged (e.g. Slack, Teams, Help Desk, etc.)
Instructions
1. This End User Support Plan template should be initiated during the “Build” phase of the Okta Deploy Methodology. 2. Once the Okta design implementation is underway, Okta's Customer PM, Okta Business Analyst (if staffed), or designee should develop the End User Support Plan with other project team members using the "End User Support Plan Template" tab in this workbook as a guide. 3. Okta's Customer PM, Okta Business Analyst (if staffed), or designee should list the different levels of support, the example support activities expected, the user types, the tools and methods available and their hours of support, the responsible teams and the associated access levels required, any support materials that need to be developed, and escalation paths to cover the Okta products and features that are being implemented. Think beyond just the people on or involved with the project team as well, such as downstream impacted users in a B2B or B2C use case.
Best Practices
Examples of popular support methods are: Slack channels, war rooms, internal sites, help desk, Okta Dashboard notices, tech events/"Days".
Subsequent Steps
1. Once Okta's Customer PM, Okta Business Analyst (if staffed), or designee has completed the End User Support Plan, it should be reviewed with the entire customer project team and all identified responsible support teams. 2. Any support material development activities should be added to the overall End User Change Management Plan. 3. Okta's Customer PM, Okta Business Analyst (if staffed), or designee should also begin executing this End User Support Plan.

## End User Support Plan Template
Issue Level | Example Tasks | User Type | Tool/Method | Operating Hours/Dates | Responsible Team & Associated Access Levels Required | Support Materials Required for Responsible Teams | Escalation Path | Comments
<L1 L2 L3 Etc..> | <Application access Logging in Setting up MFA options Enrollment in self-service password reset Account lockout and recovery Temporary password assistance MFA reset via App admin console Etc...> | <Internal Employee External Partner Okta's Customer's Customer Etc..> | <Slack Channel War Room Internal Site Help Desk Okta Dashboard Notice Tech Event/"Days" Etc..> |  | <IT Help Desk App SMEs Etc..> | <Knowledge Objects Standard Operating Procedure Event posters/flyers/handouts Quick reference guides Etc...>